WORK PLANS

Appendix N – Reduce Rates of Chronic Disease

Mississippi has a public health crisis. In 1996, 19.8% of the adult population was obese. By 2013, the obesity prevalence in our population had increased to 35.2%. If the tide is not changed, the percent of obesity in our population will reach over 50% by 2024. Obesity is a root cause of most chronic illnesses. Therefore, it is the role and obligation of Public Health to inform and educate Mississippians about this threat to their health just as it does when there is a threat of pandemics and epidemics. The consequences of obesity are Type 2 diabetes, heart disease, arthritis, stroke, and dementia. Currently in Mississippi, 1.1 million adults and 126,000 children are obese; many of whom already show signs of chronic illnesses. Unnecessary suffering is being caused by obesity, which is mainly driven by sedentary lifestyles and unhealthy eating habits. According to the CDC, 75% of total health care expenditures are associated with treating chronic diseases. If Mississippians reduce their BMI rates to lower levels and achieve an improved status of health, the state could save over $13 billion annually in unnecessary health care costs.

APPENDIX N: Mississippi State Community Scorecard – 2016  
PRIORITY AREA #3: Reduce Rates of Chronic Disease

Goal 3.1 Decrease obesity rates through the promotion of healthy lifestyles

**Strategic Objective 3.1.1** Increase the percent of youth ages 17 and under who engage in 60 minutes of daily physical activity

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Red: Not On Target | | | Yellow: Falling Behind | | | Green: On Target | |
| **Measure** | | **Baseline** | **Current/ Date** | | **Target** | **Critical Actions/Intervention Strategies** | | **Status R/Y/G** | |
| Percentage of students in grades 9-12 who achieve 1 hour or more of moderate and/or vigorous intensity physical activity daily  *Data Source: YRBS* | | 2013:  25.9% |  | | 2019:  28.5% | Establish and/or enhance school, community, and home environments that support physical activity  a. Use data collected by MDE to assess implementation of physical activity requirements for the Healthy Students Act among schools, including capacity by May 2017.  b. Identify databases that track and monitor the number  of youth ages 2 to 5 that engage in physical activity by December 2016.  c. Establish 10 new Mayoral Health Councils who will promote: shared use agreements and complete streets by December 2016. | | a. Red – Action Needs Revision per MDE.  b. Green – No statewide database exists at this time, but studies were presented that is tracking this data within target population.  c. Green | |
| Organization/ Lead Person: a. Estelle Watts, Office of Healthy Schools, MDE; b. Dr. Lei Zhang, Office of Health Data and Research, MSDH;  c. Dr. Victor Sutton, Office of Preventive Health, MSDH | | | | | | | | | |

APPENDIX N: Mississippi State Community Scorecard – 2016  
PRIORITY AREA #3: Reduce Rates of Chronic Disease

Goal 3.1 Decrease obesity rates through the promotion of healthy lifestyles

**Strategic Objective 3.1.1** Increase the percent of youth ages 17 and under who engage in 60 minutes of daily physical activity

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of municipalities that offer opportunities for organized physical activity  *Data Source: Office of  Preventive Health* | 2013:  25.9% |  | January 2020:  28.5% | d. Conduct an environmental scan to determine the number and location of shared use agreements, organized sports, and complete streets by December 2016  e. Create and implement an educational awareness campaign to decrease screen time by December 2016  f. Provide four educational messages on physical activity and nutrition in parents and kids magazines to promote awareness of physical activity and nutrition by May 2017 | d. Green  e. Yellow  f. Yellow |
| Organization/ Lead Person: d. Tiffani Grant, Office of Preventive Health, MSDH; e. Liz Sharlot, Office of Communications, MSDH; f. Liz Sharlot, Office of Communications, MSDH | | | | | |

**Strategic Objective 3.1.2** Increase the percent of adults ages 18-64 who engage in at least 150 minutes of weekly   
moderate intensity physical activity

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of adults ages 18 and older who achieve at least 150 minutes a week moderate-intensity aerobic physical activity or 75 minutes a week of vigorous-intensity aerobic activity (or an equivalent combination)  *Data source: BRFSS* | 2013:  37.4.9% |  | January 2020:  39.0% | Establish and/or enhance community and worksite environments that support physical activity  a. Establish 10 new Mayoral Health Councils who will promote: shared use agreements, complete streets, and built environment supports by December 2016  b. Conduct an environmental scan to determine the number and location of shared agreements, organized sports, and complete streets by December 2016 | a. Green  b. Green |
| Organization/ Lead Person: a. Dr. Victor Sutton, Office of Preventive Health, MSDH; b. Tiffani Grant, Office of Preventive Health, MSDH; c. Cassandra Dove, Office of Preventive Health, MSDH; d. Dr. Dan Jones, UMMC Center for Obesity Research; e. Mary Jane Coleman (interim), Office of Health Promotion and Health Equity, MSDH | | | | | |

APPENDIX N: Mississippi State Community Scorecard – 2016  
PRIORITY AREA #3: Reduce Rates of Chronic Disease

Goal 3.1 Decrease obesity rates through the promotion of healthy lifestyles

**Strategic Objective 3.1.2** Increase the percent of adults ages 18-64 who engage in at least 150 minutes of weekly   
moderate intensity physical activity

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of adults ages 18 and older who achieve at least 150 minutes a week moderate-intensity aerobic physical activity or 75 minutes a week of vigorous-intensity aerobic activity (or an equivalent combination)  *Data source: BRFSS* | 2013:  37.4% |  | January 2020:  39.0% | c. Identify, adapt and disseminate, and promote a Congregational Health Ministry Toolkit for Mississippi churches to promote physical activity by December 2016  d. Share and translate Mississippi obesity research findings by December 2016  e. Engage 25 by 25 physician partnership who seek to: reduce physical inactivity by 10% and maintain the prevalence (no further increase) of diabetes and obesity  by December 2016 | c. Yellow  d. Green  e. Yellow |
| Organization/ Lead Person: a. Dr. Victor Sutton, Office of Preventive Health, MSDH; b. Tiffani Grant, Office of Preventive Health, MSDH; c. Cassandra Dove, Office of Preventive Health, MSDH; d. Dr. Dan Jones, UMMC Center for Obesity Research; e. Mary Jane Coleman (interim), Office of Health Promotion and Health Equity, MSDH | | | | | |

**Strategic Objective 3.1.3** Decrease the percentage of students in grades 9-12 who consume fruits and vegetables less than 1 time daily

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of students in grades 9-12 who consume fruit less than 1 time daily | 2013:  51.1% |  | 2019:  46.0% | Establish and/or enhance school, community, and home environments that support access to healthy food options  a. Use data collected by MDE to assess implementation of nutrition requirements for the HSA among schools, including capacity by May 2017 | a. Red – Action Needs Revision per MDE. |
| Percentage of students in grades 9-12 who consume vegetables less than 1 time daily  *Data Source: YRBS* | 2013:  44.8% |  | 2019:  40.3% |
| Organization/ Lead Person: a. Dr. Victor Sutton, Office of Preventive Health, MSDH; b. Tiffani Grant, Office of Preventive Health, MSDH; c. Cassandra Dove, Office of Preventive Health, MSDH; d. Dr. Dan Jones, UMMC Center for Obesity Research; e. Mary Jane Coleman (interim), Office of Health Promotion and Health Equity, MSDH | | | | | |

APPENDIX N: Mississippi State Community Scorecard – 2016  
PRIORITY AREA #3: Reduce Rates of Chronic Disease

Goal 3.1 Decrease obesity rates through the promotion of healthy lifestyles

**Strategic Objective 3.1.3** Decrease the percentage of students in grades 9-12 who consume fruits and vegetables less than 1 time daily

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of students in grades 9-12 who consume fruit less than 1 time daily | 2013:  51.1% |  | 2019:  46.0% | b. Identify databases that track and monitor the consumption of nutritious foods and beverages among youth ages 2 to 5 by December 2016  c. Establish 10 new Mayoral Health Councils who will promote: SNAP benefits at established farmers markets and establishing farmers markets by December 2016  d. Provide resources and tools to school health councils on health food options within all school settings and functions (Farm to School, School Gardens, and Health Concession Stand Options) by December 2016 | b. Green – No statewide database exists at this time, but studies were presented that is tracking this data within target population.  c. Green  d. Green |
| Percentage of students in grades 9-12 who consume vegetables less than 1 time daily  *Data Source: YRBS* | 2013:  44.8% |  | 2019:  40.3% |
| Organization/ Lead Person: a. Dr. Victor Sutton, Office of Preventive Health, MSDH; b. Tiffani Grant, Office of Preventive Health, MSDH; c. Cassandra Dove, Office of Preventive Health, MSDH; d. Dr. Dan Jones, UMMC Center for Obesity Research; e. Mary Jane Coleman (interim), Office of Health Promotion and Health Equity, MSDH | | | | | |

**Strategic Objective 3.1.4** Decrease the percentage of adults ages 18 and older who report consuming fruits and vegetables less than one time daily

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of adults ages 18 and older who report consuming fruit less than one time daily.  *Data source: BRFSS* | 2013:  49.9% |  | 2019:  44.9% | Establish and/or enhance community and worksite environments that support access to health food options  a. Establish 10 new Mayoral Health Councils who will promote: SNAP benefits and established farmers markets and establishing farmers markets by December 2016 | a. Green |
| Organization/ Lead Person: a. Dr. Victor Sutton, Office of Preventive Health, MSDH; b. Cassandra Dove, Office of Preventive Health, MSDH; c. Dr. David Buys, Mississippi State Extension | | | | | |

APPENDIX N: Mississippi State Community Scorecard – 2016  
PRIORITY AREA #3: Reduce Rates of Chronic Disease

Goal 3.1 Decrease obesity rates through the promotion of healthy lifestyles

**Strategic Objective 3.1.4** Decrease the percentage of adults ages 18 and older who report consuming fruits and vegetables less than one time daily

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Measure** | **Baseline** | **Current/ Date** | **Target** | **Critical Actions/Intervention Strategies** | **Status R/Y/G** |
| Percentage of adults ages 18 and older who report consuming fruit less than one time daily.  *Data source: BRFSS* | 2013:  49.9% |  | 2019:  44.9% | b. Identify, adapt and disseminate, and promote a Congregational Health Ministry Toolkit for Mississippi churches to promote access to healthy foods by  December 2016  c. Conduct healthy food preparation workshops for SNAP and WIC recipients by December 2016 | b. Yellow  c. Green |
| Organization/ Lead Person: a. Dr. Victor Sutton, Office of Preventive Health, MSDH; b. Cassandra Dove, Office of Preventive Health, MSDH; c. Dr. David Buys, Mississippi State Extension | | | | | |

Status will be reviewed using a stoplight approach as follows:

|  |  |  |
| --- | --- | --- |
| Red: Not On Target | Yellow: Falling Behind | Green: On Target |

**COORDINATING CO-CHAIRS:**  Jacquilyn German, MSDH; Dr. John Cross, UMMC

**PARTNERS AND STAKEHOLDERS:** Therese Hanna, Center for MS Health Policy; Tameka Walls, MSDH; Dr. Edward Hill, Board of Health; Dr. Alfio Rausa, MSDH; Dr. Craig Escude, MS Dept. of Mental Health; Tim Darnell, MSDH; Heather Wagner, MSDH; Anne Travis, The Bower Foundation; Cassandra Dove, MSDH; Jackie Hawkins, MSDH; Kathy Yadrick, USM College of Health; Caroline Newkirk, MSDH; Dr. David Buys, MSU Extension Service; Jennifer Downey, USM College of Health; Lisa Henick, MS Dept. of Mental Health; Roy Hart, MS Public Health Institute; Dr. Dan Jones, UMMC; DR. JOHN CROSS, UMMC; Estelle Watts, MS Dept. of Education; Dale Dieckman, MS Dept. of Education; Michael Jordan, MS Dept. of Education; Deborah Colby, Nat’l Diabetes and Obesity Research Center at Tradition; Dr. Sylvia Byrd, MSU Extension Service; John Davis, MS Dept. of Human Services; Tiffani Grant, MSDH; Dr. Lei Zhang, MSDH;